## Sheet1
category | content
title | Restructure the tests
open_at | 2021-11-23T13:22:35Z
closed_at | 2022-06-22T13:12:18Z
comment | (2021-11-23T13:22:35Z): The current tests suite has a number of issues which is slowly growing. Some notable ones are: - GitHub runners often run out of resources during the execution of the tests - Large test suites are flaky and Windows tests are even more flaky, sometimes outright not runnable - The CI takes a very long time to complete (around 10-20 minutes) - The setup is not optimized (sometimes document stores are started even if not used) - Most unit tests are actually integration tests in disguise We have a lot of margin of improvement on our test suite. The main goals are: - Separate unit tests from integration tests - Use mocks heavily in the unit tests - Increase test speed, coverage and readability To achieve these goals, I propose to: - [x] Separate `unit_tests` and `integration_tests`. - Unit tests should test only Haystack code and mock all dependencies. - If the test loses its utility in the process, then it was probably not needed to begin with and should stay as part of a larger integration test instead. - Unit tests should be really fast and always able to run locally on any reasonable laptop without GPU. - Unit tests should run in matrices of all supported Python versions and possibly all supported dependency versions, as much as possible. - https://github.com/deepset-ai/haystack/pull/2562 - Integration tests should be very few and do few asserts, - Corner cases should be rather covered by unit tests - Stuff can still be mocked in shorted integration tests. - We might want to further distinguish between integration and end-to-end tests, but this decision can be taken in a later stage. - https://github.com/deepset-ai/haystack/pull/2557 - [ ] Create some easy-to-reuse mocks for the most used and most resource intensive components of Haystack: - MockReader - MockRetriever (a MockDPRetriever might be needed too) - MockDocumentStore (maybe a simplified version of InMemoryDocumentStore) - Other components if needed will be added progressively in later PRs - [x] Refactor the fixtures and move them in the relevant suites if needed - Some fixtures are very specific for some test suites, sharing them only makes them more complex. - **In tests only**, we prefer code duplication over code reusability. Tests should be first of all very easy to read. - https://github.com/deepset-ai/haystack/pull/2577 - https://github.com/deepset-ai/haystack/pull/2554 Additional, more specific tasks include: - [ ] Each document store will have its own tests. - Reusing tests across document stores is probably the source of their really complex setup, and the differences among them are often too large for this process to bring many benefits. - We might still have some shared tests, but they should be the minority and possibly they should be only integration tests. - https://github.com/deepset-ai/haystack/pull/2573 - [x] Review the GitHub workflows - There is probably some improvements on the way the tests are executed on the CI for example about the document store containers. - https://github.com/deepset-ai/haystack/pull/2576 - https://github.com/deepset-ai/haystack/pull/2547 - https://github.com/deepset-ai/haystack/pull/2556