## Sheet1
category | content
title | Create distilled models based on TinyBERT
open_at | 2022-01-04T15:23:49Z
closed_at | 2022-01-19T14:11:49Z
comment | (2022-01-04T15:23:49Z): With #1873 and #1874 we implemented loss functions and data augmentation for knowledge distillation based on the TinyBERT paper. This issue here is about training distilled models with that technique for question answering. **Tasks:** * Create two distilled models with augmented versions of GermanQuAD and SQuAD * Compare their performance to our other distilled models and experiment with distillation parameter settings * Publish the distilled models on the model hub and also store the augmented versions of the datasets in our S3 * Update the documentation with experiment results and also with advise on when to use which of the two distillation techniques that we now have: https://haystack.deepset.ai/guides/model-distillation
(2022-01-17T12:05:13Z): With the upload of [deepset/tinybert-6l-768d-squad2](https://huggingface.co/deepset/tinybert-6l-768d-squad2), the first step of this issue has been completed. A rough estimate of the remaning steps: 1) Pretraining a German TinyBERT. To implement this, we have two options: - Training using [original implementation](https://github.com/huawei-noah/Pretrained-Language-Model/tree/master/TinyBERT): Then we would only need to do some data preprocessing. Estimate: about one day - Training using haystack implementation: It is the same as intermediate layer distillation so we would only need to implement data loading. An advantage of this would be that we could also use other models than BERT e.g. (G)Electra as teacher. Estimate: 2 to 3 days Training time: about 3.5 days with 4 GPUs (very rough estimate) 2) Augmenting GermanQuAD Here we can reuse existing script completely. Run time depends on multiplication factor, but not more than 3 hours. 3) Fine tuning German model Depends again on multiplication factor of previous step and we can again reuse existing script. Should take about 4 days with 1 GPU.
(2022-01-19T14:11:49Z): Main work is done here. Let's continue the work and discussion about pretraining further student models in #2021