## Sheet1
category | content
title | Add support for images
open_at | 2022-04-13T12:57:26Z
closed_at | 2022-11-24T10:29:36Z
comment | (2022-04-13T12:57:26Z): **Problem** So far Haystack has been focusing strongly on text-only search. However, the same architecture is likely to be effective on other mediums, such as images. This epic tracks the implementation of support for image indexing and retrieval in Haystack. **Process** - [x] Research on the topic - Candidate models for image retrieval identified: [CLIP](https://openai.com/blog/clip/) and [Data2Vec](https://huggingface.co/docs/transformers/main/en/model_doc/data2vec) - `Data2VecVision` has been chosen due to the existence of sibling models for text and audio which would allow us to have comparable embeddings across different document types later on (see #2445). - [x] Investigate and eventually adapt how Haystack loads models from HF. - #2703 - [x] Create a primitive `MultiModalRetriever` that works in isolation (NOT in a pipeline) with at least one single document store, and add tests. - #2865 - #2857 - #2891 - [x] Make `MultiModalRetriever` work on all docstores, if possible and not too time consuming. - #2866 - [x] Extend primitives (`Document`, `Answer`, etc) to account for the new data type, and add tests. (~WARNING: Big task!~ Changes might not be as big as initially assumed) - #2867 - [x] Make the `MultiModalRetriever` work in a query pipeline, and add tests. - [x] Make the `MultiModalRetriever` work in a indexing pipeline, and add tests. - [x] Create a tutorial and some documentation Later steps (not in order of importance, not blocking each other): - Implement training and evaluation on image retrieval task - https://github.com/deepset-ai/haystack/issues/3410 - Make `MultiModalRetriever` work on the REST API and/or make a separate demo for it (a mixed media one would be super-cool tho) - https://github.com/deepset-ai/haystack/issues/3623 - Image-to-text conversion, mainly designed for indexing. Note: this is independent from the rest of the changes, could be even picked up now by some brave external contributor. - #2444