## Sheet1
category | content
title | Make query endpoint ready for production workloads
open_at | 2022-12-23T07:48:50Z
closed_at | 2023-12-06T10:47:52Z
comment | (2022-12-23T07:48:50Z): **Problem Statement** As a developer running Haystack in a production environment, I want the `/query` endpoint to be scalable and reliable so that my system is stable. **User Tasks** - Pull a Docker image - Customize the default Haystack setup - Configure additional services - Configure a pipeline - Deploy the container in a pod - 🔴 The official Helm chart is not working with the new Haystack images - Ensure the container is healthy - 🔴 Pain point: we don't know if there was a problem caching the model until we use it - Receive query from user - Ensure we have enough resources to respond fast - 🔴 No idea if there's enough GPU RAM left for larger batches - 🔴 Missing guidance on Autoscaling horizontally - 🔴 Concurrency is an issue - Combine queries in batches - 🔴 Feature doesn't exist, look at other ML frameworks for inspiration - Send queries to Haystack - Run pipeline - 🟡 We suspect it can be more efficient - Get the query result - Handle result schema problems - 🔴 Schema change shouldn't go unnoticed - Send results to user - Change Haystack version - 🔴 update is risky as we don't know in advance if upgrade causes problems - ensure the deployment is healthy - 🔴 very limited service observability ```[tasklist] ### Tasks - [ ] https://github.com/deepset-ai/haystack-helm/issues/3 - [ ] https://github.com/deepset-ai/haystack-demos/issues/6 - [ ] https://github.com/deepset-ai/haystack/issues/3910 - [ ] https://github.com/deepset-ai/haystack/issues/3618 - [x] https://github.com/deepset-ai/haystack/issues/3870 - [ ] https://github.com/deepset-ai/haystack/issues/3911 - [ ] https://github.com/deepset-ai/haystack/issues/3912 - [x] https://github.com/deepset-ai/haystack/issues/3913 - [ ] https://github.com/deepset-ai/haystack/issues/3914 - [ ] https://github.com/deepset-ai/haystack/issues/3790 - [ ] https://github.com/deepset-ai/haystack/issues/3915 - [ ] https://github.com/deepset-ai/haystack-private/issues/46 ```