## Sheet1
category | content
title | Migration to new Pipeline
open_at | 2023-03-13T10:49:15Z
closed_at | 2023-07-07T12:04:23Z
comment | (2023-03-13T10:49:15Z): _Follow up of https://github.com/deepset-ai/haystack/issues/2807_ --- ## Goal Now that we have an initial implementation of the [new Pipeline](https://github.com/deepset-ai/haystack/pull/4368), we should start migrating most nodes, stores, REST API and all other abstractions to support it. ## Steps Not in priority order unless specified. - Migrate nodes. In priority order: - [x] #4462 - [ ] `WebRetriever` https://github.com/deepset-ai/haystack/issues/4840 - [ ] `Retriever`: one for each document store - [ ] #4842 and https://github.com/deepset-ai/haystack/issues/4843 - [ ] A `Reader` - [ ] File converters (txt, pdf, other formats) - [ ] `PreProcessor` - [ ] `FileTypeClassifier` - All other nodes in order of "popular demand" (like Whisper, language classifiers, image related nodes, etc), like: - `WhisperTranscriber`: https://github.com/deepset-ai/haystack/pull/4723 - Migrate `Agent` and tools. Agents will become a node and tools are probably going to be converted into nodes too. To be refined. - Migrate Stores - [x] Define a new structure for them: https://github.com/deepset-ai/haystack/pull/4370 - [x] #4446 - [x] Implement filters for `MemoryDocumentStore` : https://github.com/deepset-ai/haystack/issues/4838 - https://github.com/deepset-ai/haystack/pull/4447 - https://github.com/deepset-ai/haystack/pull/4768 - https://github.com/deepset-ai/haystack/pull/4773 - [x] #4839 - [ ] Support one or two "modern" vector stores (Qdrant/Weaviate/Pinecone) - [ ] Support Elasticsearch 8 - Migrate all other stores in order of "popular demand" (especially FAISS or SQL) - Implement REST API - [x] #4427 - [ ] Make Docker images for them - Introduce "standard pipelines", for example "QAPipeline", "IndexingPipeline", "RAGPipeline", "AgentPipeline". These pipelines are blocked by the implementation of the relevant nodes. To be refined - Documentation and tutorials for everything ```[tasklist] ### Tasks - [ ] https://github.com/deepset-ai/haystack/issues/4462 - [ ] https://github.com/deepset-ai/haystack/issues/4840 - [ ] https://github.com/deepset-ai/haystack/issues/4842 - [ ] https://github.com/deepset-ai/haystack/issues/4843 - [ ] https://github.com/deepset-ai/haystack/pull/4723 - [ ] https://github.com/deepset-ai/haystack/pull/4370 - [ ] https://github.com/deepset-ai/haystack/issues/4446 - [ ] https://github.com/deepset-ai/haystack/issues/4838 - [ ] https://github.com/deepset-ai/haystack/pull/4447 - [ ] https://github.com/deepset-ai/haystack/pull/4768 - [ ] https://github.com/deepset-ai/haystack/pull/4773 - [ ] https://github.com/deepset-ai/haystack/issues/4839 - [ ] https://github.com/deepset-ai/haystack/issues/4427 ```
(2023-04-05T01:28:26Z): Do you have a rough timeline for the release of v2 (including the new pipeline mentioned here)? As to the vector store, I'd like to vote for Qdrant. It is also among the ones supported by OpenAI's latest retrieval plugins.
(2023-07-07T12:04:23Z): Let's close this epic and continue tracking of the pipeline migration in the follow-up epic for Q3 https://github.com/deepset-ai/haystack/issues/5265 We'll continue the open tasks there too.
(2023-07-07T12:08:39Z): @jingqiao I can't communicate a timeline yet but we're focusing on this topic as our main priority for Q3. We will support Qdrant among many other document stores in v2. 🙂