## Sheet1
category | content
title | [New Homepage]
open_at | 2023-09-20T14:24:53Z
closed_at | 2023-10-26T15:57:46Z
comment | (2023-09-20T14:24:53Z): ### Why do we need this functionality? Current homepage is ouf-of-day. ### What are we developing? Redesign homepage + update information ### What are the validation criteria to validate this feature? - See Figma maquettes - On mobile and desktop with different website sizes ### What's out of scope for this feature? ### Should this feature be feature flagged? Yes. Use in growthbook the flag: 🚩 `new-homepage-activated` (boolean) ### How are we going to code this feature? #### 1- Navbar: - 1-a AAUser, when I click on sign up, I can sign up with email + pwd, email +magic link, and login with google auth - 1-b AAUser, I can see the new navbar with Log In and with Sign Up #### 2- Screen 1: - 2-a AAUser, I can see a degrade behind taking the upper left space of the homepage - 2-b AAUser, I can see the complete background (degrade + white + beige) - 2-c AAUser, I can see the text and the action calls - Get a second Brain with Quivr - Upload all your files - CTA: (no contact sales team for now) - Demo Video - 2-d AAUser, I can see the 2 superposed images #### 3- Screen 2: - 3-a: Add demo video - 3-b: Add background dark purple - 3-c: Add texts + CTA #### 4- Screen 3: - 4-a: Add white background - 4-b: Add component UseCases - 4-c: Connect UseCases components to CMS #### 5- Screen 4: - 5-a: Add beige background + purple rectangle - 5-b: Add component "What people say about Quivr" - Connect to LinkedIn and to Twitter - 5-c: Add components in the last purple rectangle: - Title + body - CTA - Links to Git + LinkedIn + Discord #### 6 - 🐞 Small fixes - 6 - a: fix slanted white gradient - 6 - b: fix testimonial too large width #### 7 - ✉️ Contact sales team - 7 - a: Redirect the CTA from the home-page to a contact-page with header (black text), testimonials and footer from home page - 7 - b: Add the form in a modal (not linked to email yet) and replace form by thank you message after clicking on the contact button - 7 - c: Add validation with react-hook-form - 7 - d: Send email from the backend with resend - 7 - e: Trigger the email from the front ### Are there any technical decisions made that should be shared? ### What is preventing us from delivering this feature? ### What can the feature potentially break?